## How to Use
OFFICE TROLL - GAME DESIGN PROJECT PLAN
Last updated: July 19, 2026 ¦ Team: Sechaba, Latita, Sandile, Sufyaan
Dashboard — High-level KPIs, phase gates, weekly focus.
Master Schedule — Original timeline + Gantt; add owners, status, deliverables per row.
Task Tracker — Break parent tasks into subtasks for daily/sprint work.
Deliverables — Formal outputs, versions, submission links.
Team & RACI — Who does what; R/A/C/I per workstream.
Design Doc Tracker — GDD section completion checklist.
Asset Pipeline — Art/audio/UI asset status through review.
Playtest Log — Sessions, bugs, severity, fix tracking.
Risks & Issues — Proactive risks + active blockers.
Meeting Notes — Standups, design reviews, decisions.
Tips:
• Set B4 (Current Date) uses =TODAY() — always current.
• Use dropdowns for Status, Priority, Discipline for consistency.
• Link Deliverables and Task Tracker IDs in Master Schedule 'Depends On' column.
• Update Dashboard weekly before stakeholder check-ins.
PROJECT SETUP (yellow cells):
• Change game title, engine, links, and team names in ONE place — Project Setup sheet.
• Master Schedule header and Owner dropdowns pull from there automatically.
TRACK AS YOU GO:
• Actual Hours (Master Schedule col R, Task Tracker col L) — log weekly.
• Depends On / Blockers — update when scope or order changes.
• Playtest Log — one row per session; link action items to Task Tracker IDs.
• Risks & Issues — raise early; assign Owner from team list.

## Project Setup
PROJECT SETUP — edit yellow cells only
Game / Working Title | Office troll
Project / Course Name | Game Design Capstone - Project Plan
Engine / Platform | Unity 6 / Windows PC
Build / Repo Link | https://github.com/sufyaanAlbertus/Work_Integrated_Learning_OfficeTroll.git
Arc / Submission Link | https://arc.yourschool.edu (PoE upload)
Project Lead | Sechaba
Team Member (dropdown source)
Sechaba
Latita
Sandile
Sufyaan
Tip: Names in rows 11–18 appear in Owner/Assignee dropdowns on other sheets.

## Dashboard
PROJECT DASHBOARD
Overall Progress | 60.36% |  | Phase 1 Progress | 100%
Tasks Complete | 4 |  | Phase 2 Progress | 74%
Tasks In Progress | 500% |  | Phase 3 Progress | 15%
Tasks Blocked | 0 |  | Design Discipline % | 91.67%
Est. Hours (Total) | 232 |  | Art Discipline % | 70%
Actual Hours (Total) | 156 |  | Next Milestone Due
Days Until Due | -74
Weeks in Progress | 2471%
PHASE CHECKLIST
Phase | Key Gate | Target Date | Owner | Status | Evidence Link
Phase 1 | Research + 2 concepts approved | 46101 |  | Sechaba | Complete
Phase 2 | GDD + UI + assets draft complete | 46129 |  | Latita | In Progress
Phase 3 | Playable vertical slice | 46136 |  | Sufyaan | In Progress
Submission | Final PoE on Arc | 46171 |  | Sechaba | Not Started
WEEKLY FOCUS (update each standup)
Week Of | Top 3 Goals | Risks | Decisions Needed
| 2026-05-26 | Lock GDD v1.0; unblock greybox; playtest #2 | Art bandwidth; build instability on lab PCs | Final concept (Concept A vs B)

## Master Schedule
GAME DESIGN PROJECT PLAN
Project Name | Game Design Capstone - Project Plan |  | Game / Working Title | Office troll
Project Start | 2026-02-27 |  | Target Ship / Due Date | 2026-06-06
Current Date | 2026-08-19 |  | Engine / Platform | Unity 6 / Windows PC
Project Lead | Sechaba |  | Build / Repo Link | https://github.com/sufyaanAlbertus/Work_Integrated_Learning_OfficeTroll.git
Weeks in Progress | 24.7143 |  | Days Until Due | -74
[19 empty] | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29
Task | Start Date | Duration (Days) | End Date | Remaining Days | Progress | Phase | Discipline | Owner | Priority | Status | % Complete | Depends On | Deliverable / Output | Acceptance Criteria | Tools / Location | Est. Hours | Actual Hours | Blockers / Notes | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task 1: Ideation & Research Report | 2026-02-27 | 7 | 2026-03-03 | 4 | 100% | Phase 1 | Production | Sechaba | Medium | Complete | 1 | - | Ideation report with 2 concepts + research | Clear problem statement; cites 3+ sources; team sign-off | Arc / Drive / Repo | 16 | 16 | bar: 2026-02-27
- Research & Root Cause Analysis | 2026-03-04 | 3 | 2026-03-06 | 2 | 100% | Phase 1 | Research | Latita | Low | Complete | 1 | Task 1 kickoff | Root cause / market research summary | RCA diagram; competitor table; player persona draft | Arc / Drive / Repo | 8 | 8 | bar: 2026-03-06
- Ideation (Two Game Concepts) | 2026-03-09 | 2 | 2026-03-13 | 4 | 100% | Phase 1 | Design | Latita | Low | Complete | 1 | Research (row 11) | Two pitch-ready game concepts (1-pagers) | Each concept: hook, genre, core loop, unique selling point | Arc / Drive / Repo | 6 | 6 | bar: 2026-03-13
- Final Task 1 Report Submission | 2026-03-14 | 5 | 2026-03-20 | 6 | 100% | Phase 1 | Documentation | Sechaba | High | Complete | 1 | Ideation (row 12) | Task 1 final report (submitted) | Meets rubric; submitted on time | Arc / Drive / Repo | 10 | 10 | Submitted on Arc | bar: 2026-03-20
Task 2: Game Design & Assets | 2026-03-19 | 12 | 2026-03-27 | 8 | 85% | Phase 2 | Design | Sechaba | Medium | In Review | 0.85 | Task 1 report (row 13) | Core loop doc + mechanics spec | Loop diagram; input map; win/lose conditions documented | Arc / Drive / Repo | 24 | 20 | bar: 2026-03-20 to 2026-03-27
- Core Gameplay & Mechanics Design | 2026-03-24 | 17 | 2026-04-03 | 10 | 90% | Phase 2 | Design | Latita | Low | In Review | 0.9 | Task 2 kickoff (row 14) | UI wireframes / mockups | All screens listed; navigation flow; accessibility notes | Arc / Drive / Repo | 40 | 36 | bar: 2026-03-27 to 2026-04-03
- User Interface (UI) Design | 2026-03-29 | 6 | 2026-04-10 | 12 | 75% | Phase 2 | UI/UX | Latita | Low | In Progress | 0.75 | Task 1 approved concepts | Character sheets + asset list | Style guide ref; export specs; naming convention followed | Arc / Drive / Repo | 16 | 12 | Waiting on final concept pick from team review | bar: 2026-04-03 to 2026-04-10
- Character & Asset Creation | 2026-04-03 | 10 | 2026-04-17 | 14 | 70% | Phase 2 | Art | Sandile | High | In Progress | 0.7 | Core mechanics draft (row 15) | Task 2 final report + asset package | All assets linked; GDD sections complete per checklist | Arc / Drive / Repo | 32 | 22 | bar: 2026-04-03 to 2026-04-17
- Final Task 2 Report Submission | 2026-04-08 | 3 | 2026-04-24 | 16 | 50% | Phase 2 | Documentation | Sechaba | Medium | In Progress | 0.5 | UI + assets (rows 16-17) | Playable prototype (vertical slice) | 5+ min playable; no blocker bugs; build runs on target platform | Arc / Drive / Repo | 8 | 4 | Draft due this week | bar: 2026-04-10 to 2026-04-24
Summative Project Submission | 2026-04-13 | 4 | 2026-05-01 | 18 | 40% | Phase 3 | Production | Sechaba | Medium | In Progress | 0.4 | Task 2 deliverables (row 18) | Refined build + changelog | Playtest feedback addressed; version tagged | Arc / Drive / Repo | 56 | 8 | bar: 2026-04-17 to 2026-05-01
- Prototype Refinement | 2026-04-18 | 14 | 2026-05-08 | 20 | 25% | Phase 3 | Engineering | Sufyaan | Low | In Progress | 0.25 | Playable prototype (row 19) | Presentation deck + demo script | 10–15 min presentation; live demo path tested | Arc / Drive / Repo | 8 | 14 | Blocked until greybox build from Riley | bar: 2026-04-24 to 2026-05-08
- Presentation Preparation | 2026-04-23 | 2 | 2026-05-15 | 22 | 10% | Phase 3 | Production | Sechaba | Low | Not Started | 0.1 | Refined build (row 20) | Peer + self evaluation forms | All forms complete per course requirements | Arc / Drive / Repo | 4 | 0 | bar: 2026-04-24 to 2026-05-15
- Peer & Self-Evaluations | 2026-04-28 | 1 | 2026-05-22 | 24 | 0% | Phase 3 | QA | Latita | High | Not Started | 0 | Presentation draft (row 21) | Final PoE on Arc | Upload confirmed; checklist 100% | Arc / Drive / Repo | 4 | 0 | bar: 2026-05-01 to 2026-05-22
- Final PoE Submission (on Arc) | 2026-05-03 | 2 | 2026-05-29 | 26 | 0% | Phase 3 | Documentation | Sechaba | Low | Not Started | 0 | Evaluations (row 22) |  |  | Arc / Drive / Repo |  | 0 | bar: 2026-05-08 to 2026-05-29
PROJECT TOTALS |  |  |  |  | 60.36% | [5 empty] | 60.36% |  |  |  |  | 232 | 156
Note on B3: Sechaba Mokoena: Insert Start Date

## Task Tracker
DETAILED TASK BREAKDOWN — use for day-to-day sprint tracking
ID | Parent Task | Subtask | Phase | Discipline | Assignee | Priority | Status | Start | Due | Est. Hrs | Logged Hrs | Remaining Hrs | Definition of Done | File / Link | Blocked? | Blocker Detail | Notes
T1.1 | Task 1 | Competitive analysis (3 games) | Phase 1 | Research | Latita | High | Complete |  |  | 4 | 4 | 0 | Table comparing mechanics, audience, monetization |  | No
T1.2 | Task 1 | Player persona + problem statement | Phase 1 | Design | Latita | High | Complete |  |  | 3 | 3 | 0 | 1 primary persona; problem validated with research |  | No
T1.3 | Task 1 | Game concept A — one-pager | Phase 1 | Design | Latita | Critical | Complete |  |  | 4 | 4 | 0 | Hook, genre, core loop, USP, target platform |  | No
T1.4 | Task 1 | Game concept B — one-pager | Phase 1 | Design | Latita | Critical | In Review |  |  | 4 | 4 | 0 | Distinct from concept A; same template |  | No
T2.1 | Task 2 | Core loop diagram | Phase 2 | Design | Latita | Critical | In Progress |  |  | 6 | 5 | 1 | Mermaid or diagram: moment-to-moment + session loop |  | No
T2.2 | Task 2 | Mechanics spec (inputs, systems, balance) | Phase 2 | Design | Latita | High | In Progress |  |  | 12 | 8 | 4 | All verbs documented; tuning knobs listed |  | No
T2.3 | Task 2 | UI flow + wireframes | Phase 2 | UI/UX | Latita | High | In Progress |  |  | 10 | 6 | 4 | All screens; HUD; menus; failure states |  | No
T2.4 | Task 2 | Character design + turnaround | Phase 2 | Art | Sandile | Medium | In Progress |  |  | 8 | 10 | -2 | Front/side; color palette; export PNG/SVG |  | No
T2.5 | Task 2 | Environment / prop asset pass | Phase 2 | Art | Sandile | Medium | In Progress |  |  | 16 | 8 | 8 | Asset list 100% with filenames + folder structure |  | No
T3.1 | Summative | Greybox / prototype build | Phase 3 | Engineering | Sufyaan | Critical | Blocked |  |  | 24 | 0 | 24 | Core loop playable 5+ minutes |  | Yes | Need approved GDD before greybox scope lock
T3.2 | Summative | Playtest session #1 | Phase 3 | QA | Latita | High | Not Started |  |  | 3 | 0 | 3 | 3+ testers; notes in Playtest Log sheet |  | No
T3.3 | Summative | Bug triage + fix sprint | Phase 3 | Engineering | Sufyaan | High | Not Started |  |  | 12 | 0 | 12 | P0/P1 bugs closed or deferred with rationale |  | No
T3.4 | Summative | Presentation + demo rehearsal | Phase 3 | Production | Sechaba | High | Not Started |  |  | 6 | 0 | 6 | Dry run recorded; backup build ready |  | No

## Deliverables
DELIVERABLES & MILESTONES
ID | Deliverable | Type | Phase | Due Date | Owner | Reviewers | Status | % Done | Submission Location | Rubric / Criteria Met? | Version | Notes
D-01 | Task 1 Final Report | Report | Phase 1 | 46101 | Sechaba | Instructor | Submitted | 1 | https://arc.yourschool.edu (PoE upload) | No | v1.0
D-02 | Game Design Document (GDD) | Design Doc | Phase 2 |  | Latita | Team Lead | In Review | 0.85 | https://github.com/sufyaanAlbertus/Work_Integrated_Learning_OfficeTroll.git | No | v0.9 | See Design Doc Tracker
D-03 | UI Mockup Package | Art/Design | Phase 2 |  | Latita |  | In Review | 0.75 | Figma — add link | No | v0.8
D-04 | Asset Package (characters, UI, audio) | Art | Phase 2 |  | Sandile |  | In Progress | 0.7 | https://github.com/sufyaanAlbertus/Work_Integrated_Learning_OfficeTroll.git | No | v0.7
D-05 | Task 2 Final Report | Report | Phase 2 | 46129 | Sechaba | Instructor | Draft | 0.5 | https://arc.yourschool.edu (PoE upload) | No | v0.5
D-06 | Playable Prototype Build | Build | Phase 3 | 46136 | Sufyaan | Team | In Progress | 0.25 | itch.io / build folder | No | v0.2
D-07 | Presentation Deck | Presentation | Phase 3 | 46150 | Sechaba | Class | Not Started | 0.05 | Slides — add link | No | v0.1
D-08 | Final PoE Submission | Submission | Phase 3 | 46171 | Sechaba | Instructor | Not Started | 0 | https://arc.yourschool.edu (PoE upload) | No | v0.0

## Team & RACI
TEAM ROSTER & RACI
TEAM ROSTER
Name | Role | Discipline | Email / Contact | Availability (hrs/wk) | Primary Responsibilities
Sechaba | Project Lead | Design / Production | sechabamokoena10@gmail.com | 10 | Reports, milestones, presentations
Latita | Game Designer | Design | latita.mvunelo@gmail.com | 12 | GDD, mechanics, UI wireframes, playtests
Sandile | Artist | Art | sandiledube11@gmail.com | 10 | Characters, UI art, asset pipeline
Sufyaan | Programmer | Engineering | Sufyaan.albertus040@gmail.com | 12 | Prototype, builds, bug fixes
RACI MATRIX (R=Responsible, A=Accountable, C=Consulted, I=Informed)
Workstream | Lead | Designer | Artist | Programmer | QA | Instructor
Research & ideation | A | R | I | I | I | C
Core mechanics design | A | R | C | C | I | C
UI/UX | A | R | C | C | I | I
Art & assets | A | C | R | I | I | I
Prototype build | A | C | C | R | C | I
Playtesting | A | R | I | R | R | I
Reports & submission | A | R | I | I | C | C

## Design Doc Tracker
GDD / DESIGN DOCUMENTATION TRACKER
Section | Required? | Owner | Status | % Complete | Last Updated | Doc Link | Review Notes
Executive summary / elevator pitch | Yes | Sechaba | Approved | 1
Design pillars & goals | Yes | Latita | Approved | 1
Target audience & personas | Yes | Latita | Approved | 1
Competitive analysis | Yes | Sufyaan | Approved | 1
Core loop (moment + session) | Yes | Sufyaan | In Review | 0.9
Mechanics & systems | Yes | Sufyaan | In Review | 0.85
Controls / input map | Yes | Sufyaan | Draft | 0.5
Progression & economy | Optional | Latita | Draft | 0.4
Level / content design | Optional | Latita | In Review | 0.75
UI/UX specification | Yes | Sandile | Approved | 1
Art style guide & references | Yes | Sandile | Not Started | 0
Audio direction | Optional | Latita | Draft | 0.3
Technical constraints & platform | Yes | Sufyaan | Approved | 1
Risk register (design) | Yes | Sechaba | Draft | 0.6
Playtest plan | Yes | Latita | Draft | 0.4
Appendix: change log | Yes | Sechaba | Not Started | 0

## Asset Pipeline
ASSET PIPELINE
Asset ID | Name | Category | Spec (size/format) | Assigned To | Status | Priority | Due | File Path / Link | In Build? | Review Status | Notes
A-001 | Player character sprite | Character | 32x32 PNG | Sandile | Approved | High |  |  | Yes | Approved
A-002 | Main menu background | UI | 1920x1080 | Sufyaan | Ready for Review | Medium |  |  | Yes | Pending
A-003 | HUD elements kit | UI | Vector/SVG | Sufyaan | WIP | High |  |  | Partial | Pending
A-004 | SFX — UI click | Audio | WAV 44.1kHz | Sandile | Not Started | Low |  |  | No | Pending
A-005 | BGM loop — gameplay | Audio | OGG loop | Sandile | WIP | Medium |  |  | No | Pending

## Playtest Log
PLAYTEST & QA LOG
Session # | Date | Build Version | Tester(s) | Session Goal | Method | Findings (summary) | Severity | Action Item | Owner | Status | Fixed In Build
1 | 2026-04-10 |  | Classmates (n=3) | Core loop clarity | Think-aloud | 2/3 confused by objective marker | UX | Add HUD objective ping | Sufyaan | Fixed | v0.15
2 | 2026-05-18 |  | QA + design (n=5) | Difficulty curve | Survey | Boss too hard; avg 8 min session | Balance | Tune boss HP | Latita | In Progress
3 | 2026-05-28 |  | External (n=4) | Onboarding + fun | Remote | Strong art; 1 quit before tutorial end | Fun / Engagement | Shorten tutorial | Sechaba | Open
4
5
6

## Risks & Issues
RISK & ISSUE REGISTER
ID | Type | Description | Impact | Likelihood | Score | Mitigation | Owner | Status | Date Raised | Target Resolution
R-01 | Risk | Scope too large for prototype deadline | High | Medium | 6 | Cut optional mechanics; prioritize vertical slice | Sechaba | Monitoring | 2026-03-15
R-02 | Risk | Art pipeline bottleneck | Medium | High | 6 | Use placeholder art early; lock style guide week 1 | Sandile | Mitigated | 2026-03-20
I-01 | Issue | Build fails on lab PCs — missing runtime | High | — |  | Repro steps documented; assign programmer | Sufyaan | Open | 2026-04-01 | 2026-04-15

## Meeting Notes
MEETING & STANDUP NOTES
Date | Meeting Type | Attendees | Agenda | Decisions | Action Items | Next Meeting
2026-07-21 | Online | Sufyaan,Latita,Sandile,Sechaba | Nest playtest and what our game is missing | Playtest at the next Rosebank game jam and collect feedback |  | 2026-07-30
2026-08-11 | Online | Sechaba,Sufyaan ,Sandile | Submission for phase 1&2 | Take feedback from playtests and try implement changes |  | 2026-08-26